## Blad1
List with decisions |  | International Management in Schools
| Date |  |  | Decision | [5 empty] | End date
1. | 2017-10-10 |  |  | Change the meeting schedule |  |  |  | reason
|  |  |  | 1. The Netherlands |  | TPM |  | The situation in Sint Maarten,
|  |  |  | 2. Poland |  | Blended |  | because of the hurricane.
|  |  |  | 3. Spain |  | Blended
|  |  |  | 4. Lithuania |  | TPM
|  |  |  | 5. France |  | Blended
|  |  |  | 6. Sint Maarten |  | Blended
|  |  |  | 7. The Netherlands |  | TPM
| 2017-10-10 |  |  | Putting the date of the first three meetings
|  |  |  | 1. The Netherlands |  | 9-12-oct. 2017
|  |  |  | 2. Poland |  | 21-27 jan. 2018
|  |  |  | 3. Spain |  | 22-28 apr. 2018
| 2017-10-10 |  |  | Students involvement in mobilities
|  |  |  | It is possible to take students to the 2nd |  |  |  | Poland would like to have a
|  |  |  | meeting in Poland. |  |  |  | real blended mobility
not only students from Sint Maarten.
| 2017-10-10 |  |  | Spanish students involvement in the
2nd mobility in Poland
|  |  |  | The Polish school will send a letter |  |  |  | It is not clear according to the rules
|  |  |  | of invitation to the Spanish school |  |  |  | if Spanish students are able to come to this meeting
|  |  |  | in order to ask students to be |  |  |  | because we did not apply for extra mone for students
|  |  |  | present at the meeting, too. |  |  |  | in this meeting. The question is if it can be paid from
the management allowance.
| 2017-10-10 |  |  | Number of students involved in a
blended mobility
|  |  |  | It is decided that 3 or 4 students of each |  |  |  | This according to the aplication and the number of
|  |  |  | country can participate in a blended |  |  |  | availible host families.
mobility
| 2017-10-10 |  |  | Possible date for the 4th meeting in
Lithiuania (TPM)
|  |  |  | End of September 2018 |  |  |  | The money is availible already because it is
the second project year
| 2017-10-10 |  |  | Creating the project website
|  |  |  | The Netherlands will do so |  |  |  | In the application is stated that we should involve
|  |  |  | by Angela Bogaard |  |  |  | students from universities/ it decreases the tasks
of the coordinator a bit
email: angela_bogaard@hotmail.com
| 2017-10-10 |  |  | Monitoring the project
|  |  |  | Angela Bogaard will monitor the project |  |  |  | It adds to her education to be actually
|  |  |  | as stated in the application form |  |  |  | involved in an international project.
an outsider would be asked to do so.
| 2017-10-10 |  |  | Distribution of tasks
|  |  |  | This remains the same as in the application: |  |  |  | We found out this was double work. Also
|  |  |  | exept there will be no parents magazine, for |  |  |  | we would like to use less paper.
we will publish all news on our projects
|  |  |  | website. | and Facebook.
|  |  |  | Special dates of our school year will be send |  |  |  | To have an overview of each others |  | 2017-11-15
|  |  |  | to the Polish school to create a two year calender |  |  |  | school year.
| 2017-10-10 |  |  | A letter of change in the programme | [5 empty] | 2017-10-25
|  |  |  | The Dutch school will provide each partner |  |  |  | For major changes should be reported
|  |  |  | school with the changes in the schedule |  |  |  | to the National Agencies.
in order to inform all National Agencies.
| 2017-10-10 |  |  | Internationalisation policy in school
|  |  |  | The Dutch school will provide their | [5 empty] | 2017-11-15
internationalisation policy in school
in English to the other schools
|  |  |  | This document will be adjusted | [5 empty] | 2018-01-20
by the other participating schools
to their needs
| 2017-10-10 |  |  | Activities in the project
|  |  | 1. | Activities can be carried out
by two schools (minimum)
or six schools (maximun)
Everything between two and six is possible
|  |  | 2. | We are going to start with the |  |  |  | This because of the education reform in
|  |  |  | 13-14-15 years old students |  |  |  | Poland. This age group is able to work on the
project in this school year, not in the next one
|  |  | 3. | Reading of the suggestions made |  |  |  | For they have don the most specific |  | 2017-10-11
|  |  |  | by the Spanish partner school |  |  |  | work to start with
|  |  | 4. | To make a project not only for
the two project years, but als for the
| 2017-10-10 |  |  | years to come. More influence of
management in schools.
| 2017-10-11 |  | 5. | Heroes and super-heroes will
be the first topic
| 11-10-2-17 |  | 6. | One local hero and one super |  |  |  | To keep it interesting for the students |  | 2017-11-15
hero will be chosen by all
schools
| 2017-10-11 |  | 7. | The choice of the heroes |  |  |  | To keep it central |  | 2017-11-15
will be send to Niek
| 2017-10-11 |  | 8. | A comic/strip/catoon will |  |  | then |  |  | 2017-11-16
start in Poland
[8 empty] | 2. | The Netherlands | 2018-01-05
6 boxes of each country
[8 empty] | 3. | Lithuania | 2018-02-20
[8 empty] | 4. | France | 2018-04-05
[8 empty] | 5. | Spain | 2018-05-20
[8 empty] | 6. | Sint Maarten | 2018-06-30
|  |  | 9. | Poland will send apps |  |  |  | Different ways to make a poster |  | 2017-11-15
about creating a poster
Each country choses one
app for the workshop
|  |  | 10. | The making of posters
During the blended mobility in
Poland there will be
presentations of each country
abou there hero's.
Then there will workshops how
to make posters
Then as a final product
posters will be made by
the students
Partner involvement during a
blended mobility
During a blended mobililty
all partner school will present
what has been done in their school.
If possible this will be done by
students.